## Summary
The purpose of this document is to describe detailed configuration for [CLIENT]'s ThousandEyes deployment. This guide accompanies the Implementation Plan.
Follow up requests may be sent directly to the document author, or to services@thousandeyes.com.
Change Control
Title: | Implementation Plan Details
Customer Name
Engagement ID
Version: | 0.1
Date of version:
Created by:
Confidentiality level: | Confidential
Resources
Name | Contact | Company | Title
Version History
Date | Description of Change | Created By | Version | Recording

## Package Details
Professional Services Packages
Level of service and deliverables for AS-Fixed ‘Users’
Level of service and deliverables for AS-Fixed ‘Units’
Level of service and deliverables for AS-Fixed ‘Insights’
Level of support service and deliverables included in ThousandEyes product purchase
ThousandEyes Legacy Support Services
Deliverable | Insights ASF-CORE-TE-INSGHT | Users ASF-CORE-TE-USERS | Units ASF-CORE-TE-UNITS | AS-T Custom
Enterprise agent configuration | No | No | YES, ≤5 enterprise agents | User defined
Endpoint agent installation guidance | No | YES, ≤500 endpoint agents | No | User defined
Package and catalog configuration | Yes, all | No | No | User defined
Organizational settings configuration | Yes | Yes | Yes | Yes
Test creation | No | ≤10 tests | ≤60 non-synthetic tests | User defined
≤ 1 synthetic test
Label instrumentation | No | Yes | Yes | User defined
Deployment | Yes | Yes | Yes | Yes
Planning and data collection | Yes | Yes | Yes | Yes
Alert rules | ≤ 10 rules | ≤ 10 rules | ≤ 10 rules | User defined
Dashboards | ≤ 2 dashboards | ≤ 2 dashboards | ≤ 2 dashboards | User defined
Reports | ≤ 2 reports | ≤ 2 reports | ≤ 2 reports | User defined
Alert integration | No | No | No | User defined
Data integration | No | No | No | User defined

## Implementation Roadmap
Complete | Under Construction | Roadblocks

## Project Plan - Users (hidden)
Task Name | Owner | Status | Priority | Start | Finish | % Completed | Notes | Extra Comments
Pre KO Call (Internal Organization)
Create Project Plan |  | In Progress |  |  |  | 10%
Internal Sync |  | In Progress |  |  |  | 100% | 0316: Internal Sync w/CSM & engineer to be up to date about the account status.
Collect licensing Info | [5 empty] | 0%
Collect ORG ID /Name | [5 empty] | 0%
Collect POV Documents |  | Not Started | High |  |  | 25% | 0316:Waiting for CSM to schedule KO with the customer
Update Kick-off Presentation |  | Not Started
Customer Kick-off |  | Not Started | High
Customer Kick-off
Identify Stakeholders | [5 empty] | 50%
Identify Main Point of Contact | [5 empty] | 0%
Identify Service / Use Case Owners | [5 empty] | 0%
Identify Knowledge Transfer Session Users/Groups | [5 empty] | 0%
Confirm Use Cases | [5 empty] | 0%
Schedule Recurring Check-ins | [5 empty] | 0%
Implementation Plan
Implementation Plan Creation | [5 empty] | 0%
Implementation Plan Presented to Customer | [5 empty] | 0%
Implementation and Deployment
Account Set Up | [5 empty] | 0%
Configure SSO | [5 empty] | 10%
Configure Account Groups | [5 empty] | 0%
Configure Quotas | [5 empty] | 0%
Define Account Groups using Endpoint Agents | [5 empty] | 0%
Define Roles for Endpoint Agent Deployment
Firewall Rules/Proxy Configuration
Identify Endpoint Agent Installation Options
Discuss Browser Extentions
Define TCP/ICMP Testing or Both | [5 empty] | 0%
Identify VPN
Define Endpoint Labels | [5 empty] | 0%
Enbale Automated Session Testing | [5 empty] | 0%
Define Monitored Networks | [5 empty] | 0%
Define Monitored Domain Sets | [5 empty] | 0%
Configure Tests | [5 empty] | 0%
Determine Dashboard Requirements | [5 empty] | 0%
Dashboard Creating | [5 empty] | 0%
Dashboard Scheduling | [5 empty] | 0%
Dashboard Snapshots | [5 empty] | 0%
Determine Alert Rules & Settings | [5 empty] | 0%
Configure Alert Rules | [5 empty] | 0%
Alert Notification Settings | [5 empty] | 0%
Project Closure
Implementation Knowledge Transfer | [5 empty] | 0%
PS-CSM Hand off Documentation | [5 empty] | 0%
Hand off Meeting | [5 empty] | 0%
OVERALL PROJECT COMPLETION | 0.5556%

## Project Plan - Insights (hidden)
Task Name | Owner | Status | Priority | Start | Finish | % Completed | Notes | Extra Comments
Pre KO Call (Internal Organization)
Create Project Plan |  | In Progress |  |  |  | 10%
Internal Sync |  | In Progress |  |  |  | 100% | 0316: Internal Sync w/CSM & engineer to be up to date about the account status.
Collect licensing Info | [5 empty] | 0%
Collect ORG ID /Name | [5 empty] | 0%
Collect POV Documents |  | Not Started | High |  |  | 25% | 0316:Waiting for CSM to schedule KO with the customer
Update Kick-off Presentation |  | Not Started |  |  |  | 0%
Customer Kick-off |  | Not Started | High
Customer Kick-off
Identify Stakeholders | [5 empty] | 0%
Identify Main Point of Contact | [5 empty] | 0%
Identify Service / Use Case Owners | [5 empty] | 0%
Identify Knowledge Transfer Session Users/Groups | [5 empty] | 0%
Confirm Use Cases | [5 empty] | 0%
Schedule Recurring Check-ins | [5 empty] | 0%
Implementation Plan
Implementation Plan Creation | [5 empty] | 100%
Implementation Plan Presented to Customer | [5 empty] | 0%
Implementation and Deployment
Account Set Up | [5 empty] | 10%
Configure SSO | [5 empty] | 0%
Configure Account Groups | [5 empty] | 100%
Configure Quotas | [5 empty] | 0%
Enable Catalog Packages | [5 empty] | 0%
Configure Tests | [5 empty] | 0%
Determine Dashboard Requirements | [5 empty] | 0%
Dashboard Creating | [5 empty] | 0%
Dashboard Scheduling | [5 empty] | 0%
Dashboard Snapshots | [5 empty] | 0%
Determine Alert Rules & Settings | [5 empty] | 0%
Configure Alert Rules | [5 empty] | 0%
Alert Notification Settings | [5 empty] | 0%
Project Closure
Implementation Knowledge Transfer | [5 empty] | 0%
PS-CSM Hand off Documentation | [5 empty] | 0%
Hand off Meeting | [5 empty] | 0%
OVERALL PROJECT COMPLETION | 8.462%

## Project Plan - Units (hidden)
Task Name | Owner | Status | Priority | Start | Finish | % Completed | Notes | Extra Comments
Pre KO Call (Internal Organization)
Create Project Plan |  | In Progress |  |  |  | 10%
Internal Sync |  | In Progress |  |  |  | 100% | 0316: Internal Sync w/CSM & engineer to be up to date about the account status.
Collect licensing Info | [5 empty] | 0%
Collect ORG ID /Name | [5 empty] | 0%
Collect POV Documents |  | Not Started | High |  |  | 25% | 0316:Waiting for CSM to schedule KO with the customer
Update Kick-off Presentation |  | Not Started |  |  |  | 0%
Customer Kick-off |  | Not Started | High |  |  | 0%
Customer Kick-off
Identify Stakeholders | [5 empty] | 0%
Identify Main Point of Contact | [5 empty] | 0%
Identify Service / Use Case Owners | [5 empty] | 0%
Identify Knowledge Transfer Session Users/Groups | [5 empty] | 0%
Confirm Use Cases | [5 empty] | 0%
Schedule Recurring Check-ins | [5 empty] | 0%
Implementation Plan
Implementation Plan Creation | [5 empty] | 0%
Implementation Plan Presented to Customer | [5 empty] | 0%
Implementation and Deployment
Account Set Up | [5 empty] | 0%
Configure SSO | [5 empty] | 0%
Configure Account Groups | [5 empty] | 0%
Configure Quotas | [5 empty] | 0%
Identify Enterprise Agent Installation Option | [5 empty] | 0%
Install Enterprise Agents | [5 empty] | 0%
Firewall Rules/Proxy Configuration | [5 empty] | 0%
Configure Notifications for Agent | [5 empty] | 0%
Define Cloud Agents for Testing | [5 empty] | 0%
Configure Label for Agents | [5 empty] | 0%
Configure Tests | [5 empty] | 0%
Determine Dashboard Requirements | [5 empty] | 0%
Dashboard Creating | [5 empty] | 0%
Dashboard Scheduling | [5 empty] | 0%
Dashboard Snapshots | [5 empty] | 0%
Determine Alert Rules & Settings | [5 empty] | 0%
Configure Alert Rules | [5 empty] | 0%
Alert Notification Settings | [5 empty] | 0%
Project Closure
Implementation Knowledge Transfer | [5 empty] | 0%
PS-CSM Hand off Documentation | [5 empty] | 0%
Hand off Meeting | [5 empty] | 0%
OVERALL PROJECT COMPLETION | 0%

## Use Cases (hidden)
Use Cases Review
Use Case | What do we need? | - | URL Details | From which locations you want to monitor? | Frequency | Are there any SLAs to create Alerts? | Who will have access to this Data? (Dashboard construction) | Progress % | Benefits
Monitor your online platforms | URL(s) | [6 empty] | 50% | This will help you identify any issues with your website, mobile app or API, and provide you with real-time visibility into user experience.
Monitor third-party services | URL - Third-party services such as cloud providers, collaboration tools (MS Teams, webex, zoom, etc. )and other service providers | [6 empty] | 0% | Monitor the performance of these services and ensure that they are meeting the service level agreements (SLAs)
Monitor branch connectivity | Agents installed on desired locations + Firewall Configuration | [6 empty] | 0% | ThousandEyes can be used to monitor the connectivity between the branches and the data center, ensuring that the network is performing optimally.Underlay and overlay connectivity
Monitor cloud services - SaaS Apps | URL(s) | [6 empty] | 0% | Monitor the performance of cloud services such as AWS, Azure, and GCP, and ensure that they are meeting SLAs.
Monitor DNS and CDN performance | URL(s) /Domains / DNS Servers (Internal) | [6 empty] | 0% | Monitor application response times, transaction volumes, and other metrics to ensure that your applications are performing optimally.
Monitor network security | Prefixes, ASN | [6 empty] | 0% | Detect and respond to any security threats in real-time, ensuring that your customers' data is protected
Hybrid Working | Endpoint Agent Installed including TCP Driver and Browser Extensions + URL(s) | [6 empty] | 0% | Monitor network performance in real-time, detect any latency issues and identify the root cause of any issues that arise.
Multi-Step Transactions (“Synthetics”) | BrowserBot intalled on Agents + Transaction Flow | [6 empty] | 0% | Transaction tests help identify performance or availability issues before they impact end users. By monitoring critical transactions, you can detect anomalies, such as slow page loads, failed logins, or error messages, and receive alerts in real-time.
VoIP Infrastructure | SIP Servers / Enterprise Agents (Simulated voice data stream ) | [6 empty] | 0% | Proactively manage voice call quality, troubleshoot network issues efficiently, and ensure optimal user experience for voice communications.

## Agent Site List
Agent Setup Deployment
Agent Type | Agent Name | Cluster Name | Proxy | Details | Status | Router
[6 empty] | Switch | Yes | Virtual Appliances | Online
[6 empty] | Raspberry | No | Cisco Devices | Offline
[8 empty] | Physical Appliances | In Progress
Raspberry Pi
Linux Package
Docker
Amazon Web Services

## Tests Details
Cloud and Enterprise Deployment
[9 empty] | Status | Test types | Interval
Units Projected Utilization % | 1% | [7 empty] | Completed | agent-to-server | 120
[9 empty] | In Progress | agent-to-agent | 300
Test Details | [8 empty] | Not Started | bgp | 600
Test Type | Test Name | Target Server/ Prefix () | Agents | Interval (sec) | Labels | Dashboards | Deployment Status | Notes |  | http-server | 900
[10 empty] | page-load | 1800
[10 empty] | web-transactions | 3600
ftp-server
dns-trace
dns-server
dns-dnssec
sip-server
voice (RTP Stream)
Note on D10: BGP Tests Prefix: a.b.c.d is a network address, with the prefix length defined as e. Prefixes can be any length from 8 to 24 Agent to Server Tests Server: target name or IP address Agent to Agent & RTP Stream Tests Target Agent: agentId of the target agent for the test DNS tests Domain: target record for test, suffixed by record type (www.thousandeyes.com CNAME). If no record type is specified, the test will default to an ANY record. dnsServers: array of DNS Server objects {“serverName”: “fqdn of server”} Web Tests url: target for the test Transaction Script: JavaScript of a web transaction test. Quotes must be escaped (precede " characters with \ ). FTP Server url: url of site being tested. Based on the request type, may be a fully qualified domain + file name (for download), a path on an FTP Server (for list and upload types) requestType: [Download, Upload, List] username: username to be used to authenticate with the destination server password: password to be used to authenticate with the destination server. SIP Server port: port number for the chosen protocol (1024..65535) sipRegistrar: SIP server to be tested, specified by domain name or IP address targetSipCredentials: target SIP server parameters targetSipCredentials.port: port number for the chosen protocol (1024..65535) targetSipCredentials.sipRegistrar: SIP server to be tested, specified by domain name or IP address .
Note on E10: Array of agent objects: agentName1,agentName2,..

## Alerts & Dashboards
Alert Details
Alert Type | Alert Name | Strategy | Conditions | Frequency | Severity | Alert Notification
Agent
Cloud and Enterprise Agents
Cloud and Enterprise Agents
Cloud and Enterprise Agents
Cloud and Enterprise Agents
Cloud and Enterprise Agents
Cloud and Enterprise Agents
Endpoint Agents
Endpoint Agents
Endpoint Agents
BGP Routing
BGP Routing
BGP Routing
Internet Insights
Internet Insights
Internet Insights
Internet Insights
Internet Insights

## Endpoint Details
Endpoint Deployment
Details
Endpoint Advantage Licenses
Endpoint Agent Essentials Licenses
Endpoint Deployment | Responsibility | Details | Status | Notes
Deployment Schedule & Method | Customer | Estimated x agents; deploying all at once? What is the deployment method - SCCM, CLI, GPO, Manually, etc? | 5%
Network Schematics | Customer | Are all of the agents remote? Are they using a VPN, or a proxy? Full tunnel or split tunnel? Is ICMP blocked? Wifi or Ethernet or both? Which browser(s) do they use? | 0%
Agent Groupings | Customer | Do all agents belong to the same group/unit/BU? Are we splitting up by geographic location, or by company department? This is needed for the testing perspective, but labeling for reports. | 0%
Testing Targets per Group | Customer | Up to 10/4* tests can be scheduled for automate data collection per agent, based on groupings; can be either web or network targets. See "Use Cases/Testing" tab. *Depend on Type of Licenses | 0%
Top Web Domains for Monitoring | Customer | Provide a list of the top 50 visited domains / websites / browser-based apps | 0%
Test Details
Test Type | Test Name | Target | Interval (sec) | Agents | Prioritized | Enabled | http-server | Interval
[7 empty] | agent-to-server | 120
[7 empty] | Automated Session Test | 300
600
900
1800
3600

## Internet Insights Details
Internet Insights Deployment | [5 empty] | No
Completed
Available Licences | [5 empty] | In Progress
Status | [5 empty] | Risk to Completion
Package Name | Data Type | Provider Type | Region | Active | Critical ISP or Applications that need specific monitoring?
North America CDN Providers | Network | CDN | North America
North America DNS Providers | Network | DNS | North America
North America IAAS Providers | ApplicationNetwork | IAAS | North America
North America ISPs | Network | ISP | North America
North America SaaS Providers | Application | SAAS | North America
North America SECaaS Providers | Network | SECAAS | North America
North America UCaaS Providers | ApplicationNetwork | UCAAS | North America
Asia/Pacific CDN Providers | Network | CDN | Asia Pacific
Asia/Pacific DNS Providers | Network | DNS | Asia Pacific
Asia/Pacific IAAS Providers | ApplicationNetwork | IAAS | Asia Pacific
Asia/Pacific ISPs | Network | ISP | Asia Pacific
Asia/Pacific SaaS Providers | Application | SAAS | Asia Pacific
Asia/Pacific SECaaS Providers | Network | SECAAS | Asia Pacific
Asia/Pacific UCaaS Providers | ApplicationNetwork | UCAAS | Asia Pacific
EMEA CDN Providers | Network | CDN | EMEA
EMEA DNS Providers | Network | DNS | EMEA
EMEA IAAS Providers | ApplicationNetwork | IAAS | EMEA
EMEA ISPs | Network | ISP | EMEA
EMEA SaaS Providers | Application | SAAS | EMEA
EMEA SECaaS Providers | Network | SECAAS | EMEA
EMEA UCaaS Providers | ApplicationNetwork | UCAAS | EMEA
Latin America CDN Providers | Network | CDN | Latin America
Latin America DNS Providers | Network | DNS | Latin America
Latin America IAAS Providers | ApplicationNetwork | IAAS | Latin America
Latin America ISPs | Network | ISP | Latin America
Latin America SaaS Providers | Application | SAAS | Latin America
Latin America SECaaS Providers | Network | SECAAS | Latin America
Latin America UCaaS Providers | ApplicationNetwork | UCAAS | Latin America

## Account Set Up
Account Setup Deployment
Time Settings
Web UI Timezone
Notification & Snapshots Timezone
SCIM Settings
Account Group
Roles
Single Sign-On
Enabled
Configuration Type
Login Page URL
Logout Page URL
Identity Provider Issuer
Service Provider Issuer
Account Groups
Account Groups | Use Case / Purpose
| Default Roles |  |  | Custom Roles
Permission | Organizational Admin | Account Admin | Regular User | <> Organizational Admin | <> Account Admin | <> Regular User
Accept inbound live shares | x | x
API access | x | x | x
Assign agent to account group | x
Assign email address of users to alerts | x | x
Assign management permissions | x
Be able to view my own saved events | x | x | x
Can add or modify tests to consume over 100% resources | x | x
Create live shares for inside the organization | x | x
Create live shares for outside the organization | x | x
Create saved events | x | x | x
Create snapshot shares | x | x | x
Create web transaction tests | x | x
Delete account | x
Download Endpoint Agents | x | x
Edit agent notifications | x | x
Edit agents in account group | x | x
Edit alert rules | x | x
Edit alert suppression windows | x | x
Edit all account groups | x | x
Edit BGP monitors | x
Edit dashboard templates for all users in account group | x | x
Edit dashboards for all users in account group | x | x | x
Edit default timezone settings | x | x
Edit device notifications | x
Edit endpoint agent monitored domain sets. | x | x
Edit endpoint agent monitored networks | x | x
Edit endpoint agent settings | x | x
Edit endpoint tests | x | x
Edit Internet Insights - Catalog settings | x | x
Edit labels | x | x
Edit live shares sent by all users in account group | x | x
Edit live shares shared by ThousandEyes | x | x
Edit my domains | x | x
Edit organization and account group quotas | x
Edit own dashboard snapshots |  |  | x
Edit own dashboard templates |  |  | x
Edit own dashboards |  |  | x
Edit own live shares |  |  | x
Edit own saved events |  |  | x
Edit own saved events for all users in account group | x | x
Edit own snapshots |  |  | x
Edit Path Visualization interface groups | x | x
Edit payment and contact details | x
Edit roles | x
Edit security & authentication settings | x
Edit snapshots for all users in account group | x | x
Edit snapshots shared by all users in account group | x | x
Edit streaming integrations | x | x
Edit Test Templates | x
Edit tests | x | x
Edit user email addresses | x | x
Edit users |  | x
Edit users in all account groups | x
Embed own widgets |  |  | x
Embed widgets for all users in account group | x | x
Internet Insights - Catalog settings | x | x | x
Keep session alive on auto-update | x | x | x
Login via Single Sign-On | x | x | x
Login via ThousandEyes login page | x | x | x
Set dashboard template as account group default | x | x
Set report template as account group default | x | x
View activity log for all users in account group | x | x
View agent notifications | x | x | x
View agents in account group | x | x | x
View alert rules | x | x | x
View alert suppression windows | x | x | x
View all account groups settings | x
View all users | x | x
View BGP monitors | x | x | x
View billing | x
View dashboards | x | x | x
View device notifications | x | x | x
View endpoint agent data | x | x | x
View endpoint agent monitored domain sets | x | x | x
View endpoint agent monitored networks | x | x | x
View endpoint agent settings | x | x | x
View endpoint data that identifies Endpoint Agents | x | x | x
View endpoint data that identifies network | x | x | x
View endpoint data that identifies users | x | x | x
View endpoint data that identifies visited pages | x | x | x
View endpoint tests | x | x | x
View labels | x | x | x
View live shares shared by ThousandEyes | x | x | x
View live sharings from all users in account group | x | x
View my domains | x | x | x
View organization usage | x
View own activity log |  |  | x
View own live shares |  |  | x
View own snapshots |  |  | x
View roles | x
View security & authentication settings | x
View sensitive data in web transaction scripts | x | x
View snapshots | x | x | x
View snapshots shared by all users in account group | x | x
View streaming integrations | x | x | x
View Test Templates | x | x | x
View tests | x | x | x
View user activity in all account groups | x

## Integrations
Integrations
Note: Integration is shared and all data entered will be visible across all your account groups.
Status
Alert Custom Webhook Integration | [6 empty] | Connected
Failed
Name | Status | URL | Authentication | Headers | URL Query Parameters | Body Requirements
Webex App Test
Tests Recommendations
AppDynamics Integration
Name
AppDynamics Instance
Auth Type Basic
Auth Type Oauth Client Credentials
AppDynamics Username
AppDynamics Password
Test Recommendations
Token URL
Client ID
Client Secret
Token
Connect to alert notifications service
Application Name
Severity | Info / Warn / Error
Tier
Node
Business Transaction

## Enterprise Agents
The test is the basic unit in the ThousandEyes platform. You'll set up tests to monitor services that your customers and employees use. Tests are categorized by what kind of agent runs the test, and by layers of operation
Link
Common Requirements
Common Requirements | With BrowserBot | Without BrowserBot
CPU Count | 2 | 2
RAM | 2 GB | 1 GB
Hard Disk Space | 20 GB | 20 GB
Network Interface | Required | Required
Internet Connection | Required | Required
Available Options
Virtual Appliances | How to Set Up the Virtual Appliance
Cisco Devices | Cisco Device Support Matrix
Physical Appliances | Installing a Physical Appliance
Raspberry Pi | Installing an Enterprise Agent on a Raspberry Pi Device
Linux Package | Enterprise Agent Deployment Using Linux Package Method
Docker | Docker Agent Configuration Options
Amazon Web Services | IaaS Enterprise Agent Deployment - Amazon AWS

## Supported Tests by Agents
Each Agent will have different requirements based on the type of device (virtual appliance, physical appliance, Cisco device etc) the agent is being installed on, and the type of installation (Docker, linux package etc). The test is the basic unit in the ThousandEyes platform. You'll set up tests to monitor services that your customers and employees use. Tests are categorized by what kind of agent runs the test, and by layers of operation.
Note: Review the Enterprise Agent tabs for your Enterprise Agent/s before continuing with the installation process.
Layer | Tests | Cloud Agents | Enterprise Agents | Endpoint Agent
Routing | BGP | ü | ü
Network | Agent to Server | ü | ü | ü
| Agent to Agent | ü | ü
DNS | DNS Server | ü | ü
| DNS Trace | ü | ü
| DNSSEC | ü | ü
Web | HTTP Server | ü | ü | ü
| Page Load | ü | ü**
| Transaction | ü | ü**
| FTP Server | ü | ü
Voice | SIP Server | ü | ü
| RTP Stream | ü | ü
**BrowserBot required
**Note: ThousandEyes component BrowserBot is not supported for Raspberry Pi implementations. This means that the Enterprise Agent on Raspberry Pi cannot run page load tests and transaction tests. All other Agents are capable to Run All Tests
**Note: Depending on the Cisco Devices, they will Required an SSD in order to Perform Page load and Transaction Tests --> Review Cisco Support Matrix to view more details for the devices that Support Browser Tests
DNA Advantage License Holder
For customers with existing Cisco DNA Advantage licenses (purchased before April 6th, 2021), see the Requisition Guide to access your embedded Cisco ThousandEyes entitlements included in your subscription.
Requisition Guide - https://www.cisco.com/c/en/us/products/collateral/switches/catalyst-9000/nb-06-cat-9k-og-cte-en.html
New Cisco DNA Advantage License Holders - When DNA Advantage licenses are purchased, or additional ThousandEyes licenses are purchased through the Cisco GPL, all Cisco Smart Account administrators associated with the organization will receive a welcome email. The account can be activated by following the "Activate your account" link in the email.

## Firewall Configuration
Firewall configuration for Enterprise Agents
Direction assumes dynamic or stateful packet filtering (pseudo-stateful, in the case of stateless protocols like UDP and ICMP) which would permit the returning packets automatically. If your firewalling or filtering device uses static packet filters, you must create rules in both directions of the communication. More details can be found here:
Firewall Configuration for Enterprise Agents
Protocol | Port | Destination | Direction | Description
TCP | 53 | * | outbound | DNS Server tests
UDP | 53 | * | outbound | DNS queries
TCP | 80 | * | outbound | Web tests
UDP | 123 | NTP servers | outbound | NTP time synchronization
TCP | 443 | * | outbound | Web tests
ICMP | n/a | * | outbound1 | ICMP-based Network Layer Agent to Server tests, Path Visualization
TCP | 443 | 192.150.160.0/24 and 208.185.7.0/24 | outbound | Agent connection to ThousandEyes Collector and API
TCP | 80 | yum.thousandeyes.com or apt.thousandeyes.com | outbound | Linux package updates2
TCP | 8998 | 127.0.0.1 | inbound | Browserbot
TCP/UDP | 5060 | * | outbond | SIP Server Tests
UDP | As per Server Port field on Advanced Settings tab of the Voice Layer's RTP Stream Test. Default = 49152 | Other Enterprise or Cloud Agents | inbound/ outbound | Voice Layer Metrics
TCP and UDP | As per Server Port field on Advanced Settings tab of the Agent to Agent Test. Default = 49153 | Other Enterprise or Cloud Agents | inbound/ outbound | Agent to Agent tests
TCP and UDP | 9119 and 9120 | ntrav.thousandeyes.com | outbound | NAT traversal for TCP/UDP-based Agent to Agent tests
Notes
1 - For the Path Visualization layer, be certain that your routers and firewalls do not block ICMP time-tolive (TTL) exceeded messages (ICMP type 11) returning to the Enterprise Agent (inbound direction) if you want Path Visualization beyond your router or firewall. Both packet filtering rules and NAT rules (if NAT is used) will need to allow for ICMP TTL exceeded messages from the target to the Enterprise Agent.
2 - Enterprise Agents automatically perform periodic updates. Ubuntu-based systems use the apt.thousandeyes.com repository; Red Hat and CentOS-based systems use the yum.thousandeyes.com repository. These repositories should be specified by hostname (not IP address), as they are cloudbased (hosted by a CDN) and are location-optimized to ensure maximum throughput. If your firewall or filtering device cannot dynamically resolve a hostname for a filter rule, you may need to manually determine the IP addresses periodically using a tool such as DIG or NSLOOKUP, and update the filter rule.